## Sheet1
Event Gantt Chart Template
Event / Activity Title Here
Project Manager - Your Name Here
Activity |  | Lead | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Post event activity
|  |  | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-05 | 2023-07-06 | 2023-07-07 | Event Takes Place Saturday July 8
Planning and evaluation | Agree upon the event objectives and measures of success | John Smith | bar: 2023-03-03
| Determine meetings schedule | Helen Jones | bar: 2023-03-03
Assign leads for each task / group of tasks | bar: 2023-03-10
Complete draft budget | bar: 2023-03-17
Draft program for event | bar: 2023-03-17
Get approval from management for program | bar: 2023-03-24
Identify measures of success (number of attendees, etc.)
Create event summary report for management
Guest list / attendance | Draft guest list | bar: 2023-03-31; 2023-04-28
Organize event registration / RSVP process | bar: 2023-05-05
Send invitation / publicize event | bar: 2023-05-12
Collect RSVPs | bar: 2023-05-19 to 2023-06-23
Confirm any special access requirements | bar: 2023-06-16 to 2023-06-23
Print guest list | bar: 2023-06-30
Identify any VIP attendees and special requirements | bar: 2023-06-30
Follow up communication with key contacts
Program | Draft event program
Confirm event host(s)
Book entertainment/music
Brainstorm and research potential speakers
Identify speaker availability
Produce speaker briefings
Arrange speaker transport
Organize accommodation
Appoint speaker liaison for the event day
Confirm final program
Send thank yous to speakers
Venue | Research potential venues | bar: 2023-03-17 to 2023-04-07
Book selected venue | bar: 2023-04-14
Confirm requirements with venue rep | bar: 2023-04-14
Organize AV/Tech | bar: 2023-04-21
Catering | Research potential caterers | bar: 2023-04-21
Select caterer and determine menu | bar: 2023-04-21
Confirm special dietary requirements | bar: 2023-06-16 to 2023-06-23
Confirm final numbers | bar: 2023-06-30
Communication | Design publicity/invitations | bar: 2023-04-21
Distribute publicity/invitations | bar: 2023-05-05 to 2023-05-12
Book event photographer | bar: 2023-05-12
Promote via social media | bar: 2023-06-30 to 2023-07-07
Post event follow-up promotion