## Dashboard
Testing Dashboard
Environment 1 |  | Environment 2
Environment 1 Test and Issue Summary |  | Environment 2 Test and Issue Summary
Testing Start | 2021-02-01 | Testing Start | 2021-03-01
Testing End | 2021-03-01 | Testing End | 2021-04-01
Total Testing Days | 28 | Total Testing Days | 31
Testing Days Remaining | 0 | Testing Days Remaining | 0
Testing Percentage Remaining | 0% | Testing Percentage Remaining | 0%
Test Plan Results |  | Test Plan Results
Pass | 1 | Pass | 0
Fail | 2 | Fail | 3
N/A | 0 | N/A | 0
(blank) | 0 | (blank) | 0
Total Tests | 4 | Total Tests | 3
% Pass and N/A | 25% | % Pass and N/A | 0%
Issue Log |  | Issue Log
Total Issues | 2 | Total Issues | 3
Resolved | 1 | Resolved | 1
Unresolved | 1 | Unresolved | 2
% Resolved | 50% | % Resolved | 33.33%
% UnResolved | 50% | % UnResolved | 66.67%
Count of UnResolved Showstopper | 1 | Count of UnResolved Showstopper | 2

## Environment 1 - Test Plan
Testing Progress | [7 empty] | Issue Progress
Test # | Test Name | Test Details | Primary Tester | Secondary Tester | Test Outcome | Date completed | Comments (if app) | Issue Details | Reported By | Reported Date | Priority | Go-Live Showstopper? | Resolved? | Resolved By | Resolved Date | Resolution Details
T1 | Test 1 | Test information | Tester Name | Other required to test | Pass | 2021-02-23
T2 | Test 2 | Test information | Tester Name | Other required to test | Fail | 2021-02-24 |  | Strange error | Name | 2021-02-25 | Low | No | Yes | Name | 2021-02-25 | Fixed it
T3 | Test 3 | Test information | Tester Name | Other required to test | Fail | 2021-02-25 |  | Errored out | Name | 2021-02-25 | Medium | Yes | No
T4 | Test 4

## Environment 2 - Test Plan
Testing Progress | [7 empty] | Issue Progress
Test # | Test Name | Test Details | Primary Tester | Secondary Tester | Test Outcome | Date completed | Comments (if app) | Issue Details | Reported By | Reported Date | Priority | Go-Live Showstopper? | Resolved? | Resolved By | Resolved Date | Resolution Details
T1 | Test 1 | Test information | Tester Name | Other required to test | Fail | 2021-02-23 |  | Couldn't login | Name | 2021-02-25 | High | Yes | No
T2 | Test 2 | Test information | Tester Name | Other required to test | Fail | 2021-02-24 |  | Strange error | Name | 2021-02-25 | Low | No | Yes | Name | 2021-02-25 | Fixed it
T3 | Test 3 | Test information | Tester Name | Other required to test | Fail | 2021-02-25 |  | Errored out | Name | 2021-02-25 | Medium | Yes | No

## Reference (hidden)
(blank)
Pass | High | Yes
Fail | Medium | No
N/A | Low

## (Archived) Detailed Task List (hidden)
Action/Task | Resource Name | Start | End | Comments | Priority H-M-L | Effort to Accomplish | Service Now Ticket
Perform P1, P2, P3 steps from Analyzer Output | Paulette/Lee/Glen | 2020-10-26 | 2020-11-06 | Waiting on direction from SCI on importance
Identify Retrofits Needed | Paulette/Lee/Glen | 2020-10-26 | 2020-11-06 | See Retrofits tab/sheet
Apply Retrofits | Paulette/Lee/Glen | 2020-10-26 | 2020-12-24
Set up and configure Oracle Assets Command Center | Glen |  |  | https://www.oracle.com/a/ocom/docs/applications/ebusiness/ebs-enterprise-command-center-quick-start-guide.pdf
Asset Reconciliation Dashboard | Glen
Asset Cost Dashboard | Glen
Asset Aging Dashboard | Glen
Asset Location Dashboard | Glen
Mass Transactions Dashboard | Glen
Additions Pipeline Dashboard | Glen
Set up and configure Payables Command Center | Paulettte
Set up and configure Receivables Command Center | Lee
Set up and configure Projects Command Center
Research SSOgen software in place of LDAP | Mark | 2020-10-07 | 2020-10-30 | Quote sent from Dave Moore SCI. ?It was decided NOT to buy SSOgen software?
High Level Review of moving Access Databases to FIS | Mark | 2020-10-13 |  | See Access Databases tab/sheet
Review 'Cost Share' Access Database for move to FIS | Mark | 2020-10-13 |  | 10/22 - Getting access - virtual box
Review 'Cost Share Staff' Access Database for move to FIS | Mark | 2020-10-13 |  | Cost share and Effort reports processes were documented by Angela Chauncey's group - I will find it and pass along
Review 'Effort Reports' Access Database for move to FIS | Mark | 2020-10-13 |  | See above comments on cost share
Effort Reporting - look at module to see if EBS can handle get get out of Access | Glen/Roger/Mark | 2020-11-05 |  | Keep Data Mart in mind
Review 'NSF HERD' Access Database for move to FIS | Mark | 2020-10-13 |  | Glen is currently working on getting files for Joni, so IT knowledge is being developed there. I also attached Joni's process instructions to that related enhancement.
Review 'Subawards' Access Database for move to FIS | Mark | 2020-10-13 |  | Joni might have documentation I can provide
Review 'Consultant' Access Database for move to FIS | Mark | 2020-10-13 |  | Joni might have documentation I can provide
Review 'Invoices New Message' Access Database for move to FIS | Mark | 2020-10-13 |  | Best documentation is probably the recorded session that Roger did on this process - Mark has listened to it.
Review 'Fixed Assets' Access Database for move to FIS | Mark | 2020-10-13
Review 'Annual Financial Report' Access Database for move to FIS | Mark | 2020-10-13
Identify Improvements to Daily Processing using new functionality
What new functionality in EBS can replace existing manual or custom functionality? Please list.
Identify Improvements to Daily Processing - these appear to be changes to current processes. Will any of these be resolved by the upgrade? MOVED TO DAILY PROCESSING IMPROVEMENT TAB | Angie/Memory/Brit/Aaron
A/P-Can the Request Set KSU AP Invoice interface w/File Checking and Single Request Payables Open Interface Import be combined into 1 Request Set | Angie/Memory/Brit/Aaron |  |  | *Can we run a GMSA pre-check/Vendor check at time of batch (In Decisions)?
A/P- As a stage two, can we also include Invoice Validation in the Request Set, but have it not complete if there are errors? | Angie/Memory/Brit/Aaron |  |  | *Stop and Need output to show what error is
Can we automate the approving to FIS process (eliminate Decisions Batching)? | Angie/Memory/Brit/Aaron |  |  | *Need to run HRIS check and Vendor check prior to batching |  | Could be a large project
Reduce clicks in Payables Manager to Confirm payment batches | Angie/Memory/Brit/Aaron
Is there a way to display all records rather than only 10 per page or view last record in the payment confirmation screen? | Angie/Memory/Brit/Aaron |  |  | Submit a Ticket Now to look into
Auto-post CC file-Send error report if exception occurs | Angie/Memory/Brit/Aaron
Draft Revenue- Combine into a Request Set | Angie/Memory/Brit/Aaron |  |  |  |  | < 2hr
Improve process messages |  |  |  | For transfer of payments
Improve process messages / error messages - Oracle Grants processes - award is supposed to now be included on output reports | Angie/Roger |  |  | • GMS: Costing and Funds Check on Straight Time Labor • GMS: Costing and Funds Check on Straight Time Labor for a Range of Projects • GMS: Distribute Supplier Cost Adjustments and Funds Check • GMS: Distribute Supplier Cost Adjustments and Funds Check for a Range of Projects • GMS: Costing and Funds Check on Usage and Miscellaneous Costs • GMS: Costing and Funds Check on Expense Report Adjustments • EXC: Transaction Exception Details by PA Period Note: Report sections applicable to Grants include Accounts Payable Invoice Exceptions, Uncosted Transactions, and Costing Exceptions • EXC: Transaction Exception Details by GL Period Note: Report sections applicable to Grants include Accounts Payable Invoice Exceptions, Uncosted Transactions, and Costing Exceptions • AUD: Supplier Costs Interface Audit • PRC: Transaction Import
Grants Processing
Automate Recalc process when IDC rate is changed or updated - (identify which burden needs to be run to eliminate duplicates) | Angie/Roger
Review how A/P transactions get marked - why some get marked and some do not (is it due to hard limits on account-manual intervention?) | Angie/Roger
Budgets - Is it a possibility of budgets being transactional? Any updates in 12.2? | Shannon/Roger/IT
Credit/Debit Memo in Accounts Receivable for Grants - Do we have the functionality? | Angie/Roger
Check Lockboxes for possibility of negative A/R's | Angie/Roger
Automate Grant Award/Project creation | Angie/Roger
Fixed Assets module capabilities -
*NEW* Collect FA Property Information at Payment Level and flow into FA module | Britt/Memory
*NEW* Capture transaction numbers associated with property numbers and display transactional detail associated with each asset | Britt/Memory
*NEW* Capture funding transaction detail associated with each asset and summarize, including TOP | Britt/Memory
*NEW* Auto assign major and minor categories | Britt/Memory
*NEW* Track CIP Payments using the subledger and use mass adds program when project is completed- Auto capture at the payment level and capture transaction detail | Britt/Memory
*NEW* Capturing CIP and Property information from AiM/Facilities Invoice Voucher | Britt/Memory
Britt/Memory
Grants module capabilities
Research & Identify the best location to capture contract numbers w/Vendors | Shannon/Roger/IT
Verify Integrations are in place and working as desired
Verfiy Check writing is working and fully compatible with printer | Paulette/Lee/Glen |  |  | See Documentation for <diagram >
Verify Discoverer Reports | Paulette/Lee/Glen
Verify Data Mart/Cube | Paulette/Lee/Glen
Verify EForms | Paulette/Lee/Glen
Verify Java Web Start | Paulette/Lee/Glen
Verify Decisions | Paulette/Lee/Glen/Shannon/Roger/Drue
Verify Project invoicing | Paulette/Lee/Glen
Project invoicing - done outside FIS. Per info from Alliance Conf - most Higher Ed users have separate systems to assist with this due to regulatory reasons This needs to work/integrate with the NEW version
Project Grant number assignment (Random number generator for Grants) |  |  |  | SPA ability to invoice: Discoverer reports 1) pulls who 2) pull invoice info to create invoice > then 'Invoices New Message' Access Database |  | very cumbersome
| Mark |  |  | Access DB, integrates into FIS - When assigning project number, |  | Needs to be rebuilt - student wrote it years ago and never finished completely. Needed updates have never been made, either.
Verify database and environment name changes
Paulette/Lee/Glen